## BAU 25-26
Exec = Chair, Vice Chair, Treasurer and CEO supported by ZA |  |  |  |  | CPA | CPA January 2025 | CPA - reviews due May 2025 & September 2025 & Janaury 2026
AHW LPCs STRATEGY – Key Objectives for workplan 25-26 (carried over from 24-25) |  |  |  |  | 2024-05-01 | 2025-01-01 | 2025-05-01
Work Strand | Subsection | Objective/ Desired Outcome | Lead | Milestones | 2024-05-01 | January 2025 and updated for 25-26 | 2025-05-01
Governance | Market Entry | Respond to all contract applications on time | ZA / FL / Regs Group | Respond within required timelines and update database | G | G
| Finance | Payplus managed payroll instigated Autumn 2023 | Review efficiency during year |  | G | G
|  | Meeting in April / May 2025 to review process going forward and any joint approach between CPA and CPHW | FL / Treasurers with Accountants | Meeting to be arranged and discussed at Joint Exec to agree way forward and office support to reduce Treasurer costs. To include possible joint account and software accounting packages | A | A
|  | Budget agreed and circulated Feb for each next financial year - split into Joint and individual taking account of NHS Funds available | Exec & Finance Group | Plan and priorities - Sept / Oct each year - Nov meeting Execs & Finance Groups - then draft budget in Jan LPC meetings for April onwards - using CPE template | G | G
|  | Treasurer reports and financial governance - reviewed alternate meetings as minimum. New Pack implemented | Treasurer & Exec & finance group | New Finance Pack implemented by April 2024 and reviewed January 2025. Checklist to form part of the self - assessment process 2-4 times a year | A | G
|  | Accounts & Annual Report prepared for each AGM in September | FL/ EC / Treasurers / ZA | Docs to Accountant mid May, 6 week completion - queries within 2 weeks and first draft within 4 weeks, final within 6 weeks - end June. AR ready for Sept. Accounts shared LPC July meeting. Sent out for sign off by early August for min 30 days ahead Sept AGMs. | A | G
|  | Meet with Accountants Feb - May | Treasurers & FL | Accountant optional for 25-26 - have internal meeting both treasurers and FL and ZA | G | G
|  | Full governance review of banking processes to ensure governance robust | Exec & Finance Group | Reviewed November 2023 - Follow up Feb 2024 - incorporate into checklist going forward 2025-26 | G | G
|  | NHS / non levy monies monitored and utilised against MOU requirements | FL / Treasurers | Reviewed November 2023 - Follow up Feb 2024 - reviewed monthly and accounted for end of fianancial year | G | G
| Internal Governance | CPA and CPHW Joint Execs | Execs & ZA | Meeting Nov and Feb each year - alternate cost of venues etc | G | G
|  | CPE - LPC RAG status complete and follow actions annually | ZA / Exec | Awaiting Governance Documents and new RAG - draft seen January 2025 and action plan started | R | A
|  | New CPE Governance Documents Implementation | Execs & ZA | Review annually February / March | G | G
|  | Members capability & capacity & ways of working. | ZA / FL | Complete biannually and for new members - next due March - May 2025 | A | A
|  | Director Insurance & ICO and Employers Insurance and CPE insurance in place |  | In place | G | G
|  | Training & Conference attendance as needed - |  | CPE Conferences - Activity Courses, Pharma, CPPE | G | G
| Subgroups | Services / Exec and subgroups to operate at LPC Meetings - approve ToR and update as CPE advice comes through | All | ToR provisional in place - review Jan 2024 - then with new CPE governace packs - completed and keep under review | A | G
| Internal Communications | Ensure clear communications within Team and handovers for leave / cover – set up and review action logs. Ensure minutes of meetings are completed, checked and added to website as agreed in timely fashion | Team | Monday.com; Box documents, backup memory sticks, basic jobs confirmed | A | A
| Record keeping | Maintain version control of all documents in use and file in agreed location accessible to the team | Team | Default - admin Box - enter all final documents monthly. Share drives for documents requiring multiple access. Database maintained daily | G | A
| Risks & Issues | Maintain a log and follow up weekly, escalate as necessary. | ZA / Team | Action Log in place to add Escalated Risks Log - shared drive - using Monday.com | G | A
|  | Maintain record of stakeholder and contractor queries – use to inform best practice and FAQ support |  | Stakeholder mapping and database to be completed for March 2023. Completed but being added to as new people appointed. Decision on external meeting notes and actions handling | G | G
| SLAs - Services | Review all old & new SLAs & RAG plus hold quarterly meetings with local service commissioners. Website checks | EC / LNH | Review annually and when come up for renewal - in progress ahead of PNA | G | A
Work Strand | Subsection | Objective/ Desired Outcome | Lead
Contractor Support | Communications | website CPE format completed - annually check all pages for accuracy. All to be trained on how to maintain it by end April 2024 | SKS | Trained by end April 2024. Access to online training for whole team as needed. Regular review of website accuracy | A | G
|  | Social media - X / facebook / LinkedIn/ Blog | SKS | work to increase posts and blogs | G | G
|  | Communication Plan - all channels: General, PQS, PCNs, CPCF etc | Team | Formalise plan in 25-26, working om WhatsApp groups | A | A
|  | Newsletters - for AHW | Team | Biweekly general comms and bimonthly Service Comms | G | G
|  | Visits & Individual support & leadership training - set up visit and call cycle at some LPC meetings. Some targetting and agree key messaging | Team | To be reinstated - calls / visits in 2024 and to continue twice a year after LPC Meetings | A | G
| Training and development | Resources - Services pack update to one pagers | EC / LNH | External Pack to be completed and shared with stakeholders | A | A
|  | Events -2 a year min - 'don’t leave money on table' and make things simple - claiming guide etc | Team | Review option for series on tutorials online | A | A
|  | Recorded training bite size and Activity PDP |  | Review options for training - negotiating first one and media training when available | A | A
|  | Implementation & increased activity | EC / LNH | Review Data weekly / monthly - contact referrers or Contractors as needed | A | G
|  | Peer support - CPD revalidation | Team | Team / LPC where required | R | G
|  | New Contract / PQS / New Services - PCARP - resources | Team | PCARP main focus | G | G
Work Strand | Subsection | Objective/ Desired Outcome | Lead
| Local Service Commissioner meetings | arrange quarterly local commissioners and review SLA - to increase value | EC/ LNH |  | G | G
Stakeholder Management | Mapping & priorities (Healthcare, Social Care, Academia, Negotiating Bodies, Commissioners, Regulatory, Pharma, MP, Councillors, Third Sector, LMC, GP Federation, PCNs, patient bodies, charities, social prescribing) | National & Regional - relationships | FL |  | G | G
|  | Stakeholder mapping | EC / LNH/ FL / ZA | Maintain database and records | A | G
|  | Local - ICS, PLACE, PCN - meeting attendance and briefing documents / bids etc |  |  | G | G
|  | Local - CC, ICB NHSEi, CPCL - meeting attendance and briefing documents / bids etc |  |  | G | G
PCN Leads – CP and within PCN – support and link working - or any new links
| Communication Plan | Newsletters and packs for stakeholders including MPs | Team | Update and review and look at external newsletters | G | A
|  | Press & Media - to be proactive and utilise CPE resources | Team | 2-3 LPC Members to be meida trained | A | A
|  | Develop Marketing Plan | Team |  | A | G
| Engagement | Representation on appropriate groups | EC / FL | Need to be on PC Collaboratives, otherwise well represented | A | A
|  | Influencing & Negotiating at all levels (training as needed) | Team | Review PDPs for training needs | R | G
| Structure | Keep under review ICS mergers etc - if planned then consider merger LPCs | FL / Exec | Review annually | G | G
|  | Transformation work | FL | As required | G | G
| Digital | IT, databases, websites etc | SKS + Team | Daily / Weekly | G | G
| Reviewing plans/ strategies / journals | Collate summarise and disseminate information | LNH / EC / FL | Undertake annually April - June | R | R
| Patients | Healthwatch & Patient Communications | ZA / Team |  | G | G
Work Strand | Subsection | Objective/ Desired Outcome | Lead
Service & Pathway Opportunities Development | Essential Services | Support meeting core and resolution issues | Team |  | A | G
|  | DMS - support | Team |  | A | G
|  | PQS - support and communications | Team | No PQS 24-25 | R | R
| Advanced Services | NMS, CPCS, Flu, Covid, GPCPCS, EDCPCS, SS, BP, Pharmacy First, OC etc | EC / LNH | See main priorites below | G | G
| Locally Commissioned Services | Retention | LNH / EC |  | G | G
|  | Development add ons | EC / LNH | extended care decommissioned | A | A
| Data sets for meetings | Agree useful data to review quarterly and produce Services Report minimum alternate LPC Meetings | LNH / EC | Services Report alt LPC Meetings | A | G
| Opportunities | Understand priorities | EC / LNH |  | G | G
|  | Develop services and business cases - DES | EC / LNH |  | A | A
|  | Local - PCN - generic | EC / LNH | n/a CW | A | A
| Implementation | Services Pack to replace PCN pack | EC / LNH | Review annually in July | G | G
|  | New Services | EC / LNH |  | G | G
|  | National - local application | EC / LNH |  | G | G
| Working with CHS | Subcontracting, opportunity appraisals | EC / LNH |  | A | A
| Council | PH other services - generic | EC / LNH |  | A | A
| Project Management | Service work and data crunching and dissemination | LNH / EC | Work on local services data | A | A
Work Strand | LPC Plan Strategy | CPA
| Workforce | Career, training, retention, cross sector - facilitation of information sharing | FL | Ongoing as needed | G | G
Local LPC Activities | Priorities - non BAU for 25-26 | PNA | All | See separate tab |  | G
|  | Self-Assessment |  | See separate tab |  | R
|  | Services related |  | See separate tab |  | A
|  | Transition CEO |  | See separate tab |  | A
|  | New CPCF |  | See separate tab |  | R
|  | Integration |  | See separate tab |  | G
| Local Relationships | Local - ICB, PLACE, PCN - meeting attendance and briefing documents / bids etc Local - CC, ICB, NHSEi - meeting attendance and briefing documents / bids etc | FL / EC / LNH | As arranged | G | G
|  | Issue resolution | ZA | As arranged
|  | Contractor – Stakeholder relationship support, intervention, | FL |  | G | G
|  | Develop network of Regional / Area Managers within Contractor base | ZA / Team | Include in biweekly comms | A | A
|  | Link to other Workforce / HCPs – Dentist / Optometrists for example | FL / EC | Annual meetings - LMC - more frequent | R | R
|  | CPCL New Leads – links into 8c role and digital transformation | FL / EC | Weekly meetings | G | G
|  | Network of patient groups and Pharma and third sector |  | Minimum annually | G | G
|  | Specialist Groups – eg Vaccinations / AMR etc | FL / EC | As arranged | G | G
HR | Clyde & Co templates in use | All in place and updated as needed - portal checked quarterly | FL / ZA | Quarterly check and update as necessary | G | G
| Objectives | Relate to Work plan areas and LPC priorities | FL for Team (Chair/ Exec for CEO) | Add priorites to work plan | G | G
| Reviews | Objective setting and annual review Jan - February ahead of joint Exec meeting. Interim reviews in Autumn ahead of November joint Exec meeting | FL for Team (Chair/ Exec for CEO) | Winter and Autumn annually | A | G
| Training and development | PDP as part of Reviews / Interim Reviews | FL for Team (Chair/ Exec for CEO) | Winter and Autumn annually | A | G

## 25-26 priorities
Priorities in addition to BAU Work Plan for 2025-2026 and beyond (set at January 2025 LPC)
Category | Activity | Lead | Outcomes Required | Budget - Levy Account or MOU Account - specify amount and source - estimates TBC | RAG | Q1 Update | Q2 Update | Q3 Update | Q4 Update
PNA | Review all PNAs in geography and border areas and feedback | FL / ZA | Full feedback on LPC area PNAs and key points for border ones especially looking at border pharmacies and impact on access | LPC Member time (Team within hours) - 5 days total for claims (1/2 day per PNA) - Levy account £5x300 = £1500
PNA | Ensure our PNAs have appropriate definitions of necessary vs desirable need vs want etc. | FL / ZA | Suitable definition based on reasonable geographical access, core hours and essential service provision but not advanced or local service provision - which can be managed by extending the range of services and number of pharmacies providing them as long as suffienciently well funded. Nor extended supplementary hours - any need can be managed by a commiddioned rota | n/a
Self-assessment LPC | Finance checklist | Exec | Use checklist to confirm all in place quarterly | n/a
Self-assessment LPC | Skills & Capacity | FL / ZA | Undertake our version annually which includes capacity | n/a
Self-assessment LPC | BAU LPC RAG | Gov Group | Complete self-assessment when final version available - twice a year | n/a
Services | Promote OC Service | EC | Resources, marketing plan, events etc to increase awareness of service and contractors to sign up and deliver as part of bundle | £10,000 - MOU
Transition | CEO retirement - smooth transition in April - June 2026 | Transition Groups - Chair and VC of each LPC + CEO | See transition group plan | £3,000 from Levy
Transition | Assess capacity of team, skills, flexibility and roles | CEO and Execs | See transition group plan & HR & Review outcomes | £1,200 from Levy
New CPCF | Actions following negotiations | All |  | £2,000 from Levy
New CPCF | Implementation of service changes / extensions | EC & Team |  | £2,000 from Levy + MOU £5,000
Integration into ICS | Representation on PC Collaborative - recognised as part of primary care | Exec & CEO | Write to Chief Exec to insist on input into PC Strategy and develop CP strategy to include within the current PC Strategy which is only focussed on GP and not been shared directly | £2,000 from Levy
Integration into ICS | Tim Sacks meetings and meetings with LRCs including LMC | Exec & CEO | Build on support from LMC, ensure not a tick box exercise | £1,200 from Levy
Integration into ICS | Write CP strategy to include in PC Strategy | All | Link with PC Strategy, wider LRCs and other sectors and CPE vision and NHs Plan | £1,000 from Levy + MOU £1,000